## CPIC Calendar
Last update :
2015-06-03 | Department of Commerce Capital Planning and Investment Control Calendar for FY 2016
Activity | Oct. | Nov. | Dec. | Jan. | Feb. | March | April | May | June | July | August | Sept.
IT Dashboard for Majors & Infrastructure/1 | Update by 10am 11th; Appeal by 25th | Update by COB 10th; Appeal by 25th | Update by 9th; Appeal by 23rd | Update by 10th; Appeal by 25th | Update by 10am 10th; Appeal by 24th | Update by 10am 10th; Appeal by 27th | Update by 10th; Appeal by 25th | Update by 10am 10th; Appeal by 25th | Update by 9th; Appeal by 26th | Update by 10am 10th; Appeal by 25th | Update by 7th 10am. Submit to OMB Aug. 11. No Appeal | 11th - Monthly Update
Baseline Change Requests | due by 11th | due by 10th | due by 9th | due by 10th | due by 10th | due by 10th | due by 10th | due by 10th | due by 9th | due by 10th. Final FY 16 BCR due 24th | No BCRs accepted until Sept. 18. | No BCRs accepted until Sept. 18.
Operational Analysis /2 |  | 17th - Annual Operational Analysis Report;
Training |  |  |  | Beginner CPIC training | [5 empty] | Beginner CPIC training
IT Budget Initiatives |  | OMB Passback after Thanksgiving |  | FY17 IT Budget due to OMB | Identify IT initiatives, Verify all IT Roadmap requirements met. |  |  | IT Budget Call. Late May submit Summary of IT initiatives | 1st, notify OUs which ones selected to brief CITRB ~ June 8
IT Portfolio, Provisioned IT, Data Center Spending |  |  | Update business cases in eCPIC to populate IT Portfolio Report | FY17 IT Budget due to OMB sometime in January |  |  | Provide feedback for draft OMB CPIC guidance | OMB CPIC Guidance Issued. |  | Late July submit all UID and investment title changes | 16th complete entering basic business case data for all IT | 6th eCPIC Lockdown; 11th submission to OMB
Major Investment and Infrastructure Business Cases; /3 | update current major IT Business Cases (MITBC) by the 12th | 3rd Complete new MITBCs including Security | Final FY18 business case update (Part A) /3 | Final FY18 Business Case Detail update in eCPIC | Final FY 18 Business Case Detail to OMB |  | Draft OMB CPIC Guidance Issued. | Final OMB CPIC Guidance Issued. | update business cases to support budget initiatives 1 week after OU budget submission. | Submit final proposed rebaselines (PBCR) for FY2017. | 16th enter/update major and non-major business cases in eCPIC | 6th - eCPIC lockdown; 11th - Submission to OMB
Non-major IT investments |  | Update all eCPIC entries for new CY appropriation '/4 | 21st; Update business cases in eCPIC per OMB Passback |  |  |  | Draft OMB CPIC Guidance Issued. | Final OMB CPIC Guidance Issued. |  | Late July identify new investments and revised status | 16th - submit all IT funding in eCPIC; 30th Draft to OMB | 6th eCPIC lockdown
Yellow indicates actions that need to be taken by operating units
/1 | Update includes actuals for milestones, performance metrics, contracts, quad chart, risk register, FAC certification, IT Security artifacts and EVM for large investments
/2 | Operational Analysis for major steady state investments
/3 | Update IT Business Case, Major IT Business Case Detail and Agency IT Portfolio data for all major and infrastructure investments whenever the current fiscal year apporpriation is enacted.
/4 | Update Non Major IT Business Case Process and Agency IT Portfolio data for all non-major investments whenever the current fiscal year apporpriation is enacted.